## Tasks
ID | WBS | Name | Duration (days) | Duration_Project | Outline_Level | Summary_YN | Milestone_YN | Predecessors | Notes
1 |  |  | 0 | 0d | 0 | N | N
2 |  |  | 0 | 0d | 0 | N | N
3 |  |  | 3 | 3d | 0 | N | N | 2
4 |  |  | 5 | 5d | 0 | N | N | 2
5 |  |  | 5 | 5d | 0 | N | N | 2
6 |  |  | 2 | 2d | 0 | N | N | 2
7 |  |  | 5 | 5d | 0 | N | N | 2
8 |  |  | 3 | 3d | 0 | N | N | 2
9 |  |  | 2 | 2d | 0 | N | N | 2
10 |  |  | 4 | 4d | 0 | N | N | 2
11 |  |  | 10 | 10d | 0 | N | N | 2
12 |  |  | 2 | 2d | 0 | N | N | 2
13 |  |  | 2 | 2d | 0 | N | N | 2
14 |  |  | 3 | 3d | 0 | N | N | 2
15 |  |  | 3 | 3d | 0 | N | N | 2
16 |  |  | 2 | 2d | 0 | N | N | 2
17 |  |  | 3 | 3d | 0 | N | N | 2
18 |  |  | 5 | 5d | 0 | N | N | 2
19 |  |  | 8 | 8d | 0 | N | N | 2
20 |  |  | 2 | 2d | 0 | N | N | 2
21 |  |  | 2 | 2d | 0 | N | N | 2
22 |  |  | 4 | 4d | 0 | N | N | 2
23 |  |  | 2 | 2d | 0 | N | N | 2
24 |  |  | 2 | 2d | 0 | N | N | 2
25 |  |  | 1 | 1d | 0 | N | N | 2
26 |  |  | 5 | 5d | 0 | N | N | 2
27 |  |  | 2 | 2d | 0 | N | N | 2
28 |  |  | 3 | 3d | 0 | N | N | 2
29 |  |  | 0 | 0d | 0 | N | N | 11,5,28,2
30 |  |  | 0 | 0d | 0 | N | N
31 |  |  | 5 | 5d | 0 | N | N | 30,29,19
32 |  |  | 4 | 4d | 0 | N | N | 30,11,5,29
33 |  |  | 3 | 3d | 0 | N | N | 30,16,2
34 |  |  | 0 | 0d | 0 | N | N | 31,32,33,29
35 |  |  | 0 | 0d | 0 | N | N
36 |  |  | 5 | 5d | 0 | N | N | 35,34,2
37 |  |  | 7 | 7d | 0 | N | N | 36
38 |  |  | 7 | 7d | 0 | N | N | 37,11
39 |  |  | 2 | 2d | 0 | N | N | 38,32,29
40 |  |  | 5 | 5d | 0 | N | N | 39
41 |  |  | 0 | 0d | 0 | N | N | 40,29,5
42 |  |  | 0 | 0d | 0 | N | N
43 |  |  | 5 | 5d | 0 | N | N | 42,17,41
44 |  |  | 60 | 60d | 0 | N | N | 43,41
45 |  |  | 0 | 0d | 0 | N | N | 44,2
46 |  |  | 0 | 0d | 0 | N | N
47 |  |  | 10 | 10d | 0 | N | N | 46,45
48 |  |  | 0 | 0d | 0 | N | N | 47

## Import_Instructions
Import this workbook into Microsoft Project (desktop)
1) File → New → blank project, or an existing template you use.
2) File → Open — if your build has 'Get Data' or 'Open from Excel' use the path below; else:
In many versions: New from Excel Workbook, or: Project → Import Wizard (may vary by SKU).
3) For **Import Export Wizard** (if shown):
- Select the **Tasks** sheet (first tab).
- Map: **Name** → Name; **Duration_Project** → Duration; **WBS** → WBS; **Predecessors** → Predecessors; **Milestone_YN** → (optional) Milestone if offered.
- **Predecessors** uses **row numbers** of other tasks in this file (1 = first data row, same as the row order in the 'Tasks' sheet, matching **ID** column in column A).
4) After import: set **Project** → **Project Information** (start date), and **Link** the schedule if not auto-calculated. Review the network diagram.
5) The XML file in this folder (MGM_Palo_to_Cisco_Actionable_Plan.xml) is an alternate; use XML **Open** if the Excel import loses links.