## Slide 1: SaC / NaC Adoption Strategy
Dhrumil Prajapati
March 2026

## Slide 2: Phases
Phase 1:
  NaC Parity collection pilot for SDWAN and Cat-C – Target EoM March 2026
Phase 2:
  Engage with customers who are scoring more than 80%** parity (Final data TBD)
Phase 3:
  Staffing arrangement and agreement on timelines and success criteria
Phase 4 (If Applicable):
  If applicable – Train LCS/BCS team and CMS team where applicable for maintain customer environment

## Slide 3: Phase 1: NaC-Parity – SDWAN and Cat-C
EN team to conduct an exercise to have all engineers run NaC-Parity tool SDWAN and Cat-C
  Target:
    Any/all customers that our team actively supports on a PID as part of PDI or Day-2
  Purpose:
    Build a database of all GES-Arch supported customers with feature parity list for SDWAN and Cat-C.
    Build a priority list of what customers can be targeted for conversation with help of theater CDAs, SDAs
    Work with theater Leaders to create a pipeline of customers with target date for Go/No-Go decision
    Establish success criteria for the outcome for customers in “Go” list
This will help us lean on low-hanging customer opportunities and build learnings from the deployment

## Slide 4: Phase 2: Engage and Strategize with customers - >80%**
Current baseline threshold – 80%** of feature parity (pending collection of data)
Any customers who are 80% or above in feature parity are candidate for conversation to use as-code methodology for their existing projects/PIDs
  The conversations will begin with 50K foot view about as-code and will be more detailed as customer is familiar with it.
  The Engineer on the account will work with SDA/Service Seller for Sales Motion
  Any resistance or concerns of not going with that method will be documented and would require further deliberation
Missing features are put in the development pipeline with a timeline of getting them fully tested and built before production rollout.
Project plan and RACI are built per architecture
Journey map is prepared for the solution adoption

## Slide 5: Phase 3: Staffing and Success Criteria
Staffing arrangement based on the Sales Motion
  Ideally, no change in existing staffing, however, addition of as-code engineer who is trained from our team, to the project for technology support.
  Objective will be to train existing architects in parallel to customer transition and build up of initial environment for the deployment
    Architects on these accounts are expected to lead with as-code delivery with demo, strategy and end-state architecture
  Success criteria is clearly defined for timely disengagement and hand-off of the responsibilities.

## Slide 6: Phase 4: As Applicable – Additional Training/Handoff
Lessons learned from THD Project:
  Additional training might be required for CMS and/or BCS/LCS team from CXC to ensure smooth transition and faster disengagement of our as-code architects
  Lab guides will be provided OR one dedicated training session will be held for entire team to focus on as-code deployment specific to customer network.
    Fundamental NaC training is out of scope and existing training materials can be leveraged.

## Slide 7: Current Delivery Process
Requirements Gathering
SRD
Network Design
SDD
Migration Strategy
Implementation Plans
Test Plans
Test Cases
Implementation
Testing
Reports
Assessment
CE/CDA Expertise - Manual
Digitized Documentation*
Network as Code*
* Depends on solution and feature availability

## Slide 8: New Delivery Process
Requirements Gathering
SRD
Network Design
SDD
Migration Strategy
Implementation Plans
Test Plans
Test Cases
Production Implementation
Testing
Reports
Technology Assessment
NaC Assessment
Lab build
NaC Lab PoC
CE/CDA Expertise - Manual
Digitized Documentation*
Network as Code*
* Depends on solution and feature availability
New Additions to our Methodology

## Slide 9: Typical NaC Feature Development Process
Issue Identification
Issue(s) Creation
Issue Assignment
Code Creation
Issue Prioritization
Code testing
PR Submission
PR Review
PR Merge
Release Schedule
High Time (~1-2 weeks)
Medium Time (~3-5 days)
Low Time (~1 day)
* Rough estimates based on patterns noted with IOS-XE, SDWAN as Code feature development

## Slide 10: In Grand Schema of Things – What do we prioritize?
Requirements Gathering
SRD
Network Design
SDD
Migration Strategy
Implementation Plans
Test Plans
Test Cases
Production Implementation
Testing
Reports
Technology Assessment
NaC Assessment
Lab build
NaC Lab PoC
Issue Identification
Issue(s) Creation
Issue Assignment
Code Creation
Issue Prioritization
Code testing
PR Submission
PR Review
PR Merge
Release Schedule